## General
Project Name: | Listing Tool
Purpose: |  | Timesheet
Description: |  | Record time spent on all activities for Listing Tool
Team Members: | 1 | Cloud Liu
| 2 | Tik Sun
| 3 | James Chen
| 4 | Wolf Yan
| 5 | Devin Yang
Document Creation Date: |  | 2015-03-20
Version: |  | 1.0

## WBS
Module | Task | SubTask | Resource | Propority | Effort (hours) | Start Date | End Date | Comments
Google AdWords API Access Application | 1. Prepare project design doc |  | Cloud |  |  | 2015-03-20 | 2015-03-20
| 2. Prepare for additional submit form |  | Cloud |  |  | 2015-03-20 | 2015-03-20
| 3. Contact with consult for further feedback |  | Cloud |  |  | 2015-03-21
|  |  | SubTotal |  | 0
eBay Item Target & Tracking | 1. Setup Interface for eBay Shopping Interface | 1.1 Update eBay service interface to be compatible with eBay shopping API | Cloud |  |  | 2015-03-18 | 2015-03-20
|  | 1.2 Create eBay shopping API | Cloud |  |  | 2015-03-18 | 2015-03-20
|  | 1.3 Create function for GetMultipleItems | Cloud |  |  | 2015-03-18 | 2015-03-20
|  | 1.4 Create EAV model for eBay GetMultipleItems result | Cloud |  |  | 2015-03-18 | 2015-03-20
|  | 1.5 Unit Test | Cloud |  |  | 2015-03-18 | 2015-03-20
| 2. Target & Tracking | 2.1 User Interface to create Target & Tracking | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.2 User Interface to List Target & Tracking | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.3 user Interface to update Target & Tracking | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.4 Miscellaneous user interface develop | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.5 Schedule job to tracking items | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.6 Schedule job to revise items if eligible | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.7 Give feedback notification if any action executed | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.8 Unit Test | Cloud |  |  | 2015-03-19 | 2015-03-20
|  |  | SubTotal |  | 0
Google AdWords API Demostration | 1. Create sub MCC acount |  | Tik |  |  | 2015-03-17 | 2015-03-20
| 2. Create sub client account |  | Tik |  |  | 2015-03-17 | 2015-03-20
| 3. Create demo Ads | 3.1 Create demo Ad campaign | Tik |  |  | 2015-03-17 | 2015-03-20
|  | 3.2 Create demo Ad group | Tik |  |  | 2015-03-17 | 2015-03-20
|  | 3.3 Create demo Ad criteria | Tik |  |  | 2015-03-17 | 2015-03-20
|  | 3.4 Create demo remarketing display Ad | Tik, James |  |  | 2015-03-17 | 2015-03-20
|  |  | SubTotal |  | 0
PayPal API Implementation | 1. PayPal API Interface |  | James |  |  | 2015-03-16 | 2015-03-20
| 2. Implement PayPal API Function | 2.1 PayPal API to initial payment | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.2 PayPal API to confirm payment | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.3 PayPal API to retrieve detail information of a transaction | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.4 PayPal API to get account status, including balance | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.5 PayPal API to make transfer | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.6 Unit Test | James |  |  | 2015-03-16 | 2015-03-20
| 3. Transaction User Interface | 3.1 User interface to initial payment | James |  | 5 | 2015-03-16 | 2015-03-20
|  | 3.2 User interface to show transaction result | James |  | 7 | 2015-03-16 | 2015-03-20
|  | 3.3 User Interface to show transaction detail | James |  | 0 | 2015-03-16 | 2015-03-20
|  | 3.4 User interface to list transaction history, with search function | James |  | 8 | 2015-03-16 | 2015-03-20
|  | 3.5 User interface to apply withdraw | James |  | 8 | 2015-03-16 | 2015-03-20
|  | 3.6 Unit Test | James |  | 0 | 2015-03-16 | 2015-03-20
|  |  | SubTotal |  | 28
Webiste Basic Function Reconstruct | 1. SSO Login | 1.1 SSO research | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 1.2 Log in & out based on cookies | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
| 2. Website layout & structure copy | 2.1 Synch CSS style from PHP site | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 2.2 Setup website structure | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 2.3 Setup website page layout | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 2.4 Localization & international | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
| 3. Log in & out function |  | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
| 4. Basic object CRUD & interface | 4.1 Company object update & view | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 4.2 User object CRUD | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 4.3 Department object CRUD | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
|  | 4.4 Notification object CRUD | Wolf, Devin |  |  | 2015-03-16 | 2015-03-20
| 5. Wish.com API Research |  | Wolf | Low |  | 2015-03-19 | 2015-03-25
|  |  | SubTotal |  | 0

## March 2010
Timesheet (March 20 ~ March 31)
Legend: |  | Planned
Overdue
Ad-hoc
|  |  | March | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL
Team Member: Cloud Liu
| No | Activity
| 1 | [16 empty] | 0
| 2 | [16 empty] | 0
| 3 | [16 empty] | 0
| 4 | [16 empty] | 0
| 5 | [16 empty] | 0
Team Member: Tik Sun
| No | Activity
| 1 | [16 empty] | 0
| 2 | [16 empty] | 0
| 3 | [16 empty] | 0
| 4 | [16 empty] | 0
| 5 | [16 empty] | 0
Team Member: James Chen
| No | Activity
| 1 | 3.1 User interface to initial payment |  | 5 | [13 empty] | 5
| 2 | 3.2 User interface to show transaction result |  | 3 |  |  |  | 4 | [9 empty] | 7
| 3 | 3.3 User Interface to show transaction detail | [15 empty] | 0
| 4 | 3.4 User interface to list transaction history, with search function |  |  | 8 | [12 empty] | 8
| 5 | 3.5 User interface to apply withdraw |  |  |  | 8 | [11 empty] | 8
Team Member: Wolf Yan
| No | Activity
| 1 | [16 empty] | 0
| 2 | [16 empty] | 0
| 3 | [16 empty] | 0
| 4 | [16 empty] | 0
| 5 | [16 empty] | 0
Team Member: Devin Yang
| No | Activity
| 1 | [16 empty] | 0
| 2 | [16 empty] | 0
| 3 | [16 empty] | 0
| 4 | [16 empty] | 0
| 5 | [16 empty] | 0
|  | TOTAL |  | 8 | 8 | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12