## General
Project Name: | Listing Tool
Purpose: |  | Timesheet
Description: |  | Record time spent on all activities for Listing Tool
Team Members: | 1 | Cloud Liu
| 2 | Tik Sun
| 3 | James Chen
| 4 | Wolf Yan
| 5 | Devin Yang
Document Creation Date: |  | 2015-03-20
Version: |  | 1.0

## WBS
Module | Task | SubTask | Resource | Propority | Effort (hours) | Start Date | End Date | Comments
Google AdWords API Access Application | 1. Prepare project design doc |  | Cloud |  |  | 2015-03-20 | 2015-03-20
| 2. Prepare for additional submit form |  | Cloud |  |  | 2015-03-20 | 2015-03-20
| 3. Contact with consult for further feedback |  | Cloud |  |  | 2015-03-21
|  |  | SubTotal |  | 0
eBay Item Target & Tracking | 1. Setup Interface for eBay Shopping Interface | 1.1 Update eBay service interface to be compatible with eBay shopping API | Cloud |  | 2 | 2015-03-18 | 2015-03-20
|  | 1.2 Create eBay shopping API | Cloud |  | 3 | 2015-03-18 | 2015-03-20
|  | 1.3 Create function for GetMultipleItems | Cloud |  | 5 | 2015-03-18 | 2015-03-20
|  | 1.4 Create EAV model for eBay GetMultipleItems result | Cloud |  | 8 | 2015-03-18 | 2015-03-20
|  | 1.5 Unit Test | Cloud |  |  | 2015-03-18 | 2015-03-20
| 2. Target & Tracking | 2.1 User Interface to create Target & Tracking | Cloud |  | 11 | 2015-03-19 | 2015-03-20
|  | 2.2 User Interface to List Target & Tracking | Cloud |  | 4 | 2015-03-19 | 2015-03-20
|  | 2.3 user Interface to update Target & Tracking | Cloud |  | 11 | 2015-03-19 | 2015-03-20
|  | 2.4 Miscellaneous user interface develop | Cloud |  | 4 | 2015-03-19 | 2015-03-20
|  | 2.5 Schedule job to tracking items | Cloud |  | 2 | 2015-03-19 | 2015-03-20
|  | 2.6 Schedule job to revise items if eligible | Cloud |  | 5 | 2015-03-19 | 2015-03-20
|  | 2.7 Give feedback notification if any action executed | Cloud |  | 2 | 2015-03-19 | 2015-03-20
|  | 2.8 Unit Test | Cloud |  |  | 2015-03-19 | 2015-03-20
|  | 2.9 Release & Test | Cloud |  |  | 2015-03-19 | 2015-03-20
|  |  | SubTotal |  | 57
Google AdWords API Demostration | 1. Create sub MCC acount |  | Tik |  | 4 | 2015-03-17 | 2015-03-20
| 2. Create sub client account |  | Tik |  | 4 | 2015-03-17 | 2015-03-20
| 3. Create demo Ads | 3.1 Create demo Ad campaign | Tik |  | 2 | 2015-03-17 | 2015-03-20
|  | 3.2 Create demo Ad group | Tik |  | 3 | 2015-03-17 | 2015-03-20
|  | 3.3 Create demo Ad criteria | Tik |  | 2 | 2015-03-17 | 2015-03-20
| 4.Create demo remarketing display Ad | 4.1 Identify your business type | Tik |  | 1 | 2015-03-17 | 2015-03-20
|  | 4.2 Create Merchant account and Link adwords accounts | Tik |  |  | 2015-03-17 | 2015-03-20 | 此处无官方例子，需要从学习所有API，测试
|  | 4.3 Create a new campaign | Tik |  | 20 | 2015-03-17 | 2015-03-20 | 此处无官方例子，需要从学习所有API，测试
|  | 4.4 Create a feed | Tik |  |  | 2015-03-17 | 2015-03-20 | 此处无官方例子，需要从学习所有API，测试
|  | 4.5 Tag your website | Tik |  |  | 2015-03-17 | 2015-03-20 | 此处无官方例子，需要从学习所有API，测试
|  | 4.6 Create dynamic ads | Tik |  |  | 2015-03-17 | 2015-03-20 | 此处无官方例子，需要从学习所有API，测试
|  | 4.7 Final checklist | Tik |  |  | 2015-03-17 | 2015-03-20
| 5.Familiar with the operation of remrketing | 5.1 capture all process and add memo | Tik |  | 3 | 2015-03-24 | 2015-03-26
|  | 5.2 Familiar with the operation of web ui process | Tik |  | 16 | 2015-03-24 | 2015-03-26
|  | 5.3 check merchant account verify url rule | Tik |  | 3 | 2015-03-24 | 2015-03-26
|  | 5.4 test to generate dynamic custome liberay for ads | Tik |  | 11 | 2015-03-24 | 2015-03-26
|  |  | SubTotal |  | 36
PayPal API Implementation | 1. PayPal API Interface |  | James |  |  | 2015-03-16 | 2015-03-20
| 2. Implement PayPal API Function | 2.1 PayPal API to initial payment | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.2 PayPal API to confirm payment | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.3 PayPal API to retrieve detail information of a transaction | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.4 PayPal API to get account status, including balance | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.5 PayPal API to make transfer | James |  |  | 2015-03-16 | 2015-03-20
|  | 2.6 Unit Test | James |  |  | 2015-03-16 | 2015-03-20
| 3. Transaction User Interface | 3.1 User interface to initial payment | James |  | 7 | 2015-03-16 | 2015-03-20
|  | 3.2 User interface to show transaction result | James |  | 13 | 2015-03-16 | 2015-03-20
|  | 3.3 User Interface to show transaction detail | James |  | 0 | 2015-03-16 | 2015-03-20
|  | 3.4 User interface to list transaction history, with search function | James |  | 22 | 2015-03-16 | 2015-03-20
|  | 3.5 User interface to apply withdraw | James |  | 9 | 2015-03-16 | 2015-03-20
|  | 3.6 Unit Test | James |  | 1 | 2015-03-16 | 2015-03-20
|  | 3.7 交易相关数据库设计 | James |  | 4 | 2015-03-16 | 2015-03-20
|  |  | SubTotal |  | 56
Webiste Basic Function Reconstruct | 1. SSO Login | 1.1 SSO research | Wolf, Devin |  | 15 | 2015-03-16 | 2015-03-20
|  | 1.2 Log in & out based on cookies | Wolf, Devin |  | 5 | 2015-03-16 | 2015-03-20
| 2. Website layout & structure copy | 2.1 Synch CSS style from PHP site | Wolf, Devin |  | 2 | 2015-03-16 | 2015-03-20
|  | 2.2 Setup website structure | Wolf, Devin |  | 2 | 2015-03-16 | 2015-03-20
|  | 2.3 Setup website page layout | Wolf, Devin |  | 2 | 2015-03-16 | 2015-03-20
|  | 2.4 Localization & international | Wolf, Devin |  | 2 | 2015-03-16 | 2015-03-20
| 3. Log in & out function |  | Wolf, Devin |  | 2 | 2015-03-16 | 2015-03-20
| 4. Basic object CRUD & interface | 4.1 Company object update & view | Wolf, Devin |  | 3 | 2015-03-16 | 2015-03-20
|  | 4.2 User object CRUD | Wolf, Devin |  | 5 | 2015-03-16 | 2015-03-20
|  | 4.3 Department object CRUD | Wolf, Devin |  | 3 | 2015-03-16 | 2015-03-20
|  | 4.4 Notification object CRUD | Wolf, Devin |  | 3 | 2015-03-16 | 2015-03-20
| 5. Wish.com API Research |  | Wolf | Low |  | 2015-03-19 | 2015-03-25 | 研究中
| 6. SSO Front And Backend | 6.1、集成第三方jar文件出现部署错误，关系依赖不能正确引用和依赖冲突，导致项目不能正常运作,集中处理jar文件的依赖关系 | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
|  | 6.2、前端项目 后端项目 sso部署、集成本地登录登出功能 | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
|  | 6.3、开发期间出现理解误区，后端登录需要通过admin 校验 | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
|  | 6.4、后台页面模板建设 | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
|  | 6.5、配置Notification | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
|  | 6.6、页面国际化 | Wolf, Devin |  |  | 2015-03-23 | 2015-03-23
| 7.调研google-api ，截取google-ui 界面，为后续工项目界面集成做准备 and 验证框架、翻译脚本 | 7.1、创建开发者账号 | Wolf |  |  | 2015-03-24 | 2015-03-24
|  | 7.2、创建广告客户账号并且关联，验证域名绑定校验 | Wolf |  |  | 2015-03-24 | 2015-03-24
|  | 7.3、获取api接口源码sdk并且阅读 | Wolf |  |  | 2015-03-24 | 2015-03-24
|  | 7.4、jquery.validate 验证表单加入框架 | Devin |  |  | 2015-03-24 | 2015-03-24
|  | 7.5、国际化页面文字，加入数据库不存在的翻译文字，整理脚本 | Devin |  |  | 2015-03-24 | 2015-03-24
|  | 7.6、准备分页 | Devin |  |  | 2015-03-24 | 2015-03-24
| 8.调研google-api 获取google 广告点击情况 and 验证框架、翻译脚本、表单验证 | 8.1、下载 google sdk 测试google代码运行测试 | Wolf |  |  | 2015-03-25 | 2015-03-25
|  | 8.2、google 获取 广告字段信息，通过字段拼写AWQL查询语句，获取google 广告点击情况 [进行中] | Wolf |  |  | 2015-03-25 | 2015-03-25
|  | 8.3、项目组部署框架，本地运行报错，出现内存溢出错误，进行修改更正[已完成] | Wolf |  |  | 2015-03-25 | 2015-03-25
|  | 8.4、初次整合项目，抽取重复的companyservice类，调整项目源码布局 | Devin |  |  | 2015-03-25 | 2015-03-25
|  | 8.5、加入分页控件，调整局部样式。 | Devin |  |  | 2015-03-25 | 2015-03-25
|  | 8.6、现分页控件为无刷新模式，预改造为每次刷新请求模式，方便引擎搜索。 局部加入表单验证 | Devin |  |  | 2015-03-25 | 2015-03-25
| 9.调研google-api 获取google 广告点击情况 目前google-sdk已经测试[通过] and 改无刷新分页为刷新分页，加入php分页样式，调整transaction页面样式，国际化页面 | 9.1、继续查看google-api获取广告的展示率和点击率 | Wolf |  |  | 2015-03-26 | 2015-03-26
|  | 9.2、由于google没有提供单纯广告的点击率和展示率，只查阅到广告系列下的广告组的点击率和展示率，目前google-sdk已经测试[通过] | Wolf |  |  | 2015-03-26 | 2015-03-26
|  | 9.3、还在进一步查看api是否提供，更深层次的费率调用[进行中] | Wolf |  |  | 2015-03-26 | 2015-03-26
|  | 9.4、调整transaction页面样式，国际化页面 | Devin |  |  | 2015-03-26 | 2015-03-26
|  | 9.5、改无刷新分页为刷新分页，加入php分页样式。 | Devin |  |  | 2015-03-26 | 2015-03-26
|  | 9.6、加入department分页和transaction分页功能 | Devin |  |  | 2015-03-26 | 2015-03-26

## March 2015
Timesheet (March 20 ~ March 31)
Legend: |  | Planned
Overdue
Ad-hoc
|  |  | March | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL
Team Member: Cloud Liu
| No | Activity
| 1 | 1.1 Update eBay service interface to be compatible with eBay shopping API |  | 2 | [13 empty] | 2
| 2 | 1.2 Create eBay shopping API |  | 3 | [13 empty] | 3
| 3 | 1.3 Create function for GetMultipleItems |  | 3 | 3 | [12 empty] | 6
| 4 | 1.4 Create EAV model for eBay GetMultipleItems result |  |  | 6 | 2 | [11 empty] | 8
| 5 | 2.1 User Interface to create Target & Tracking |  |  |  | 6 | 5 | [10 empty] | 11
| 6 | 2.2 User Interface to List Target & Tracking |  |  |  |  | 4 | [10 empty] | 4
| 7 | 2.3 user Interface to update Target & Tracking |  |  |  |  | 2 | 9 | [9 empty] | 11
| 8 | 2.4 Miscellaneous user interface develop | [6 empty] | 4 | [8 empty] | 4
| 9 | 2.5 Schedule job to tracking items | [6 empty] | 2 | [8 empty] | 2
| 10 | 2.6 Schedule job to revise items if eligible | [6 empty] | 5 | [8 empty] | 5
| 11 | 2.7 Give feedback notification if any action executed | [6 empty] | 2 | 6 | [7 empty] | 8
| 12 | 2.9 Relase & Test | [6 empty] | 2 | 3 | [7 empty] | 5
Team Member: Tik Sun
| No | Activity
| 1 | Create sub MCC acount |  | 4 | [13 empty] | 4
| 2 | Create sub client account |  | 4 | [13 empty] | 4
| 3 | Create demo Ads 3.1 |  |  | 2 | [12 empty] | 2
| 4 | Create demo Ads 3.2 |  |  | 3 | [12 empty] | 3
| 5 | Create demo Ads 3.3 |  |  | 2 | [12 empty] | 2
| 6 | Create demo Ads 3.4 |  |  | 1 | [12 empty] | 1
| 7 | Create demo remarketing display Ad 4.1 |  |  |  | 2 | [11 empty] | 2
| 8 | Create demo remarketing display Ad 4.3 |  |  |  | 6 |  | 4 | 10 | [8 empty] | 20
| 9 | 5.1 capture all process and add memo | [7 empty] | 3
| 10 | 5.2 Familiar with the operation of web ui process | [7 empty] | 8 | 8 | [6 empty] | 16
| 11 | 5.3 check merchant account verify url rule | [8 empty] | 3 | [6 empty] | 3
| 12 | 5.4 test to generate dynamic custome liberay for ads | [9 empty] | 11 | [5 empty] | 11
Team Member: James Chen
| No | Activity
| 1 | 3.1 User interface to initial payment |  | 5 | [6 empty] | 2 | [6 empty] | 7
| 2 | 3.2 User interface to show transaction result |  | 3 |  |  |  | 4 |  | 5 | 1 | [6 empty] | 13
| 3 | 3.3 User Interface to show transaction detail | [15 empty] | 0
| 4 | 3.4 User interface to list transaction history, with search function |  |  | 8 |  |  |  | 8 | 1 | 5 | [6 empty] | 22
| 5 | 3.5 User interface to apply withdraw |  |  |  | 8 |  |  |  | 1 | [7 empty] | 9
| 6 | 3.6 Unit Test | [8 empty] | 1 | [6 empty] | 1
| 7 | 3.7 交易相关数据库设计 | [7 empty] | 3 | 1 | [6 empty] | 4
Team Member: Wolf Yan
| No | Activity
| 1 | SSO Login |  | 8 | 8 | [12 empty] | 16
| 2 | 3. Log in & out function |  |  |  | 8 | [11 empty] | 8
| 3 | 5. Wish.com API Research | [5 empty] | 8 | [9 empty] | 8
| 4 | 6.1 | [6 empty] | 2 | [8 empty] | 2
| 5 | 6.1 | [6 empty] | 2 | [8 empty] | 2
| 6 | 6.3 | [6 empty] | 4 | [8 empty] | 4
| 7 | 7.1 | [7 empty] | 2 | [7 empty] | 2
| 8 | 7.1 | [7 empty] | 4 | [7 empty] | 4
| 9 | 7.3 | [7 empty] | 5 | [7 empty] | 5
| 10 | 8.1、下载 google sdk 测试google代码运行测试 | [8 empty] | 2 | [6 empty] | 2
| 11 | 8.2、google 获取 广告字段信息，通过字段拼写AWQL查询语句，获取google 广告点击情况 [进行中] | [8 empty] | 4 | [6 empty] | 4
| 12 | 8.3、项目组部署框架，本地运行报错，出现内存溢出错误，进行修改更正[已完成] | [8 empty] | 5 | [6 empty] | 5
| 13 | 9.1、继续查看google-api获取广告的展示率和点击率 | [9 empty] | 2 | [5 empty] | 2
| 14 | 9.2、由于google没有提供单纯广告的点击率和展示率，只查阅到广告系列下的广告组的点击率和展示率，目前google-sdk已经测试[通过] | [9 empty] | 4 | [5 empty] | 4
| 15 | 9.3、还在进一步查看api是否提供，更深层次的费率调用[进行中] | [9 empty] | 5 | [5 empty] | 5
Team Member: Devin Yang
| No | Activity
| 1 | 2. Website layout & structure copy |  | 8 | 8 | [12 empty] | 16
| 2 | 4. Basic object CRUD & interface |  |  |  | 8 | [11 empty] | 8
| 3 | 6.4 | [6 empty] | 2
| 4 | 6.5 | [6 empty] | 3
| 5 | 6.6 | [6 empty] | 3 | [8 empty] | 3
| 6 | 7.4 | [7 empty] | 2
| 7 | 7.5 | [7 empty] | 4
| 8 | 7.6 | [7 empty] | 5 | [7 empty] | 5
| 9 | 8.4、初次整合项目，抽取重复的companyservice类，调整项目源码布局 | [8 empty] | 2
| 10 | 8.5、加入分页控件，调整局部样式。 | [8 empty] | 4
| 11 | 8.6、现分页控件为无刷新模式，预改造为每次刷新请求模式，方便引擎搜索。 局部加入表单验证 | [8 empty] | 5 | [6 empty] | 5
| 12 | 9.4、调整transaction页面样式，国际化页面 | [9 empty] | 2
| 13 | 9.5、改无刷新分页为刷新分页，加入php分页样式。 | [9 empty] | 4
| 14 | 9.6、加入department分页和transaction分页功能 | [9 empty] | 5 | [5 empty] | 5